## Sheet1
Week | Date | Objective | Other
KW03 | 13.01-19.01 | Documentation Package, Vignette + (start) BS implementation
KW04 | 20.01-26.01 | Bootstrap + data generation
KW05 | 27.01-02.02
KW06 | 03.02-09.02 | Simulation setup/parameter
KW07 | 10.02-16.02
KW08 | 17.02-23.02 |  | Done: programming package for Thesis (ITT, Naïve Model, Bootstrap, replication of ITT, data generation)
KW09 | 24.02-02.03
KW10 | 03.03-09.03 | Run simulation
KW11 | 10.03-16.03 | First version of simulation results
KW12 | 17.03-23.03 | Re-run simulation
KW13 | 24.03-30.03 | Re-run simulation / interpret results
KW14 | 31.03-06.04 | Final version of the results (raw)
KW15 | 07.04-13.04 | First draft of results section of the paper
KW16 | 14.04-20.04 | First complete draft (plus first ever draft of discussion)
KW17 | 21.04-27.04
KW18 | 29.04-04.05 | Complete Draft
KW19 | 05.05-11.05
KW20 | 12.05 | Turn in thesis |  | Split columns writing/progeamming
Generic Milestones
Revised draft: Intro, Background, Methods |  |  |  |  | Feedback supervisors
Outline results, Outline discussion |  |  |  |  | Documentation + Vignette
Simulation code "finished" (i.e. ready to deploy) |  |  |  |  | Fill timeline
First version results (raw) |  | From here to final - may take 4 weeks looking together |  |  | Oisin TTE Papers
Re-run simulation
"Final" version results (raw)
First draft complete results section |  |  | may also take a couple of weeks
First draft discussion section
collect here; limitations, rough summary of what the results are, things you ignored and would be good for future research, relevance for people
First complete draft
Second/Third/Fourth complete draft
Aim for supervisors to at least read and give feedback on first draft, if feasible second draft